## Risks
risk_id | title | status | rating | due_date | owner_role | last_updated
1 | BCV420 Drive Pulley Fabrication | On Track | Amber | 2026-03-01 | Project Engineer | 2026-02-12
2
3
4
5

## TQs
tq_id | title | status
1 | Enduraclad Liners | Closed
2 | ROM Bin Plates | Closed
3 | Rom Bin Liners | Closed
4 | Taper Bolts | Closed
5 | ROM Liner cut outs | Closed
6 | Head chute bracker welding | Closed
7 | Isolation Deck anti-slip coating | Closed
8 | ROM Frame hole diameters | Closed
9 | ROM Ref Dim | Closed
10 | Transfer Chute hole diameter | Closed
11 | Boom conveyor skirt Ref Dim | Closed
12 | Spile bar Ref Dim | Closed
13 | Conveyor Skirt Handle | Closed
13.1 | Conveyor Skirt handle 2 | Closed
14 | Camlock and hinge details | Closed
15 | Impact loose plate | Closed
16 | BCV420 Spoon cutter liners | Closed
17 | BCV420 Head Pulley details | Closed
18 | Duablock dimensions | Closed
19 | Grizzly Billets alternative supplier | Closed
19.1 | Grizzly Billets - Secondary supplier | Open
20 | Door latch dimensions | Closed